## Project Overview
Category | Details
Project Name | F1 Historical Race Visualizer
Primary Backend | Java 21 + Spring Boot 3
Frontend | React + TypeScript + Vite
Database | PostgreSQL + TimescaleDB
Caching | Redis
Streaming | Kafka
Search | Elasticsearch
Observability | Grafana + Prometheus + OpenTelemetry
Testing | JUnit + Testcontainers + Cypress + Playwright
Deployment | Docker + GitHub Actions

## Features
Feature Area | Description
Race Replay | Play/pause/rewind/fast-forward
Timeline | Race event synchronization
Telemetry | Speed/throttle/brake/gear visualization
Analytics | Driver and constructor analytics
Championships | Dynamic standings engine
Caching | Replay snapshot caching
Streaming | WebSocket telemetry streams
Security | JWT + OAuth2
Testing | Unit/integration/e2e/performance
Data Science | Python analytics pipelines

## Requirements
Type | Requirement
Functional | Replay any historical race
Functional | Telemetry visualization
Functional | Event timeline playback
Functional | Championship tracking
Functional | Driver analytics
Non-Functional | Replay latency under 100ms
Non-Functional | Support horizontal scaling
Non-Functional | 99.9% uptime target
Non-Functional | Secure JWT authentication

## Testing Checklist
Checklist Item | Status
Unit tests for services | TODO
Repository integration tests | TODO
Kafka integration tests | TODO
Redis integration tests | TODO
Replay engine tests | TODO
WebSocket synchronization tests | TODO
Frontend component tests | TODO
E2E playback tests | TODO
Security tests | TODO
Performance benchmarking | TODO
Load testing | TODO
CI/CD pipeline verification | TODO

## Roadmap
Phase | Goals
Phase 1 | Basic backend + ingestion
Phase 2 | Replay engine
Phase 3 | Telemetry visualization
Phase 4 | Analytics + championships
Phase 5 | Distributed systems + optimization